## Tidsregistrering
TIDSREGISTRERING FOR PTE-PROJEKTET (6-3-2017 - 24-3-2017)
Dato: | Navn: |  | Rolle: |  | Aktivitet: | Starttid: | Sluttid: | Samlet tid brugt (timer):
2017-03-06 |  | Jurijs Mahtodujs (JM) |  | Any Role | Spørgsmål, roller til møde | 10:30 | 12:50 | 2:20
2017-03-10 |  | Jurijs Mahtodujs (JM) |  | Project Manager | Managing | 10:30 | 12:30 | 2:00
2017-03-10 |  | Jurijs Mahtodujs (JM) |  | Test Analyst | Test til OC4 | 11:40 | 12:00 | 0:20
2017-03-13 |  | Jurijs Mahtodujs (JM) |  | Implementer | Implementering af OC4 | 8:30 | 13:00 | 4:30
2017-03-14 |  | Jurijs Mahtodujs (JM) |  | Requirements Specifier | UC+DOM+TC | 8:15 | 9:40 | 1:25
2017-03-14 |  | Jurijs Mahtodujs (JM) |  | Requirements Specifier | AD+DD+TC | 10:00 | 11:30 | 1:30
2017-03-14 |  | Jurijs Mahtodujs (JM) |  | System Analyst | OC 7 | 12:10 | 13:00 | 0:50
2017-03-14 |  | Jurijs Mahtodujs (JM) |  | Reviewer | Review af OC6 | 13:10 | 13:40 | 0:30
2017-03-14 |  | Jurijs Mahtodujs (JM) |  | Reviewer | Review af OC7 | 13:40 | 14:20 | 0:40
2017-03-14 |  | Jurijs Mahtodujs (JM) |  | System Analyst | CD,CDC til OC5 | 14:20 | 15:10 | 0:50
2017-03-17 |  | Jurijs Mahtodujs (JM) |  | Reviewer | Review af SSD UC6 | 8:30 | 8:45 | 0:15
2017-03-17 |  | Jurijs Mahtodujs (JM) |  | System Analyst | CD,SD erVægtNormal | 9:15 | 10:20 | 1:05
2017-03-17 |  | Jurijs Mahtodujs (JM) |  | System Analyst | CD,SD erLængde2Normal | 10:20 | 11:20 | 1:00
2017-03-21 |  | Jurijs Mahtodujs (JM) |  | Reviewer | Review af OC 12 test suite | 9:30 | 10:00 | 0:30
2017-03-21 |  | Jurijs Mahtodujs (JM) |  | System Analyst | OC 12 | 10:10 | 10:40 | 0:30
2017-03-21 |  | Jurijs Mahtodujs (JM) |  | System Analyst | Samlende DOM | 13:00 | 14:40 | 1:40
2017-03-22 |  | Jurijs Mahtodujs (JM) |  | Reviewer | Review OC10 kode | 8:20 | 8:40 | 0:20
2017-03-22 |  | Jurijs Mahtodujs (JM) |  | Test Designer | j-unit test til oc4 | 8:45 | 9:20 | 0:35
2017-03-22 |  | Jurijs Mahtodujs (JM) |  | Test Designer | j-unit test til oc3 | 9:40 | 10:20 | 0:40
2017-03-22 |  | Jurijs Mahtodujs (JM) |  | Test Designer | j-unit test til normalkraft | 12:00 | 15:00 | 3:00
2017-03-23 |  | Jurijs Mahtodujs (JM) |  | Test Designer | j-unit test til normalkraft fix | 8:30 | 9:00 | 0:30
2017-03-23 |  | Jurijs Mahtodujs (JM) |  | Any Role | boejningsmoment bugfix | 13:00 | 14:00 | 1:00

## Hjælp til rollevalg
* Hvis du er i tvivl om din rolle, så kig i Appendiks A i "Rational Unified Process" (PDF side: 304 - 310) Bogen side 273 - 280)

## Deltagere
Morten K. Andersen
Steffen S. Andersen
Jeppe Damborg
Henrik S. Jørgensen
Tolga Y. Kücük
Ulla Larsen
Jurijs Mahtodujs
Christoffer A. Mørch
Maibritt R. Nielsen
Simon E.H. Nielsen
Nada H. A. Omer
Laura Poyner
Dennis K. Rasmussen
Dennis S. Rosenkilde
Allan Strange
Dan A. Toft

## Gyldige roller
Any Role
Business Designer
Business-Process Analyst
Capsule Designer
Change Control Manager
Configuration Manager
Course Developer
Database Designer
Deployment Manager
Designer
Graphic Artist
Implementer
Integrator
Management Reviewer
Process Engineer
Project Manager
Requirements Specifier
Review Coordinator
Reviewer
Software Architect
Stakeholder
System Administrator
System Analyst
Technical Writer
Test Analyst
Test Designer
Test Manager
Tester
Tool Specialist
User-Interface Designer