## Tidsregistrering
TIDSREGISTRERING FOR PTE-PROJEKTET (6-3-2017 - 24-3-2017)
Dato: | Navn: |  | Rolle: |  | Aktivitet: | Starttid: | Sluttid: | Samlet tid brugt (timer):
2017-03-06 | NO | Nada H. A. Omer |  | System Analyst | Installation af Microsoft Visio og Microsoft Project. | 8:30 | 9:50 | 1 timer : 20 minutter
2017-03-06 | NO | Nada H. A. Omer |  | System Analyst | Spørgsmål til Kundemødet. | 10:00 | 11:30 | 1 time : 30 min.
2017-03-06 | NO | Nada H. A. Omer |  | System Analyst | Rolle til kundemødet. | 12:00 | 12:45 | 0 time : 45 min.
2017-03-06 | NO | Nada H. A. Omer |  | System Analyst | Tildel Rolle til spørgsmålene til Kundemødet. | 12:45 | 12:50 | 0 time : 05 min.
2017-03-06 | NO | Nada H. A. Omer |  | System Analyst | Studere aktivetesdigram. | 13:00 | 13:45 | 0 time : 45 min.
2017-03-06 | NO | Nada H. A. Omer |  | System Analyst | Git Hub opsætning. | 14:30 | 15:30 | 1 time : 00 min.
2017-03-07 | NO | Nada H. A. Omer |  | Requirements Specifier | Visionsdokument + FURPS | 8:45 | 10:30 | 1 time : 45 min.
2017-03-07 | NO | Nada H. A. Omer |  | Requirements Specifier | Formel Use case 5 + Domæne model for UC 5 | 10:30 | 11:30 | 1 time : 00 min.
2017-03-07 | NO | Nada H. A. Omer |  | Project Manager | Iterationsplan | 12:30 | 15:20 | 2 time : 50 min.
2017-03-08 | NO | Nada H. A. Omer |  | Requirements Specifier | FURPS | 8:10 | 8:40 | 0 time : 30 min.
2017-03-08 | NO | Nada H. A. Omer |  | Requirements Specifier | Usability gools | 8:40 | 9:10 | 0 time : 30 min.
2017-03-08 | NO | Nada H. A. Omer |  | Requirements Specifier | SSD for Usecase 2 | 9:45 | 10:05 | 0 time : 20 min.
2017-03-08 | NO | Nada H. A. Omer |  | Requirements Specifier | Skabelon til OC | 13:00 | 13:10 | 0 time : 05 min.
2017-03-08 | NO | Nada H. A. Omer |  | Requirements Specifier | OC1 for angivVaegt | 13:15 | 13:45 | 0 time : 30 min.
2017-03-08 | NO | Nada H. A. Omer |  | Requirements Specifier | OC3 for beregnNormalkraft | 13:50 | 15:05 | 1 time : 15 min.
2017-03-09
2017-03-10

## Hjælp til rollevalg
* Hvis du er i tvivl om din rolle, så kig i Appendiks A i "Rational Unified Process" (PDF side: 304 - 310) Bogen side 273 - 280)

## Deltagere
Morten K. Andersen
Steffen S. Andersen
Jeppe Damborg
Henrik S. Jørgensen
Tolga Y. Kücük
Ulla Larsen
Jurijs Mahtodujs
Christoffer A. Mørch
Maibritt R. Nielsen
Simon E.H. Nielsen
Nada H. A. Omer
Laura Poyner
Dennis K. Rasmussen
Dennis S. Rosenkilde
Allan Strange
Dan A. Toft

## Gyldige roller
Any Role
Business Designer
Business-Process Analyst
Capsule Designer
Change Control Manager
Configuration Manager
Course Developer
Database Designer
Deployment Manager
Designer
Graphic Artist
Implementer
Integrator
Management Reviewer
Process Engineer
Project Manager
Requirements Specifier
Review Coordinator
Reviewer
Software Architect
Stakeholder
System Administrator
System Analyst
Technical Writer
Test Analyst
Test Designer
Test Manager
Tester
Tool Specialist
User-Interface Designer