## Tidsregistrering
TIDSREGISTRERING FOR PTE-PROJEKTET (6-3-2017 - 24-3-2017)
Dato: | Navn: | Rolle: |  | Aktivitet: | Starttid: | Sluttid: | Samlet tid brugt (timer):
2017-03-06 | Laura Poyner |  | Project Manager | Risikoanalyse | 8:30 | 13:30 | 5t
|  |  | Designer | Usecase skabelon | 13:30 | 14:00 | 30m
|  |  | Tester | Test prototype for export i Ecplise | 14:00 | 14:30 | 30m
|  |  | System Analyst | Opsæt GitHub & Visio | 14:30 | 15:30 | 1t
2017-03-07 |  |  | Requirements Specifier | Visionsdokument + FURPS | 8:45 | 10:30 | 1t 40m
|  |  | Requirements Specifier | Formel Usecase 3 + domænemodel | 10:30 | 11:30 | 1t 40m
|  |  | Project Manager | Iterationsplan 2 | 12:30 | 15:40 | 3t 10m
2017-03-08 |  |  | Requirements Specifier | FURPS | 8:10 | 8:40 | 30m
|  |  | Requirements Specifier | Usability goals | 8:40 | 9:10 | 30m
|  |  | Requirements Specifier | SSD for Usecase 2 | 9:45 | 10:05 | 20m
|  |  | Project Manager | Iterationsplan 2 | 10:10 | 14:00 | 3t 50m
|  |  | Reviewer | Review OC1 | 14:00 | 14:45 | 45m
|  |  | Requirements Specifier | Formel Usecase 3 + domænemodel | 14:45 | 15:30 | 45m
2017-03-10 |  |  | Designer | Fælles SD og DCD for OC3 | 8:05 | 10:30 | 2t 25m
|  |  | Designer | OC4 | 10:30 | 12:00 | 1t 30m
|  |  | Designer | SD og DCD for OC2 | 12:00 | 13:10 | 1t 10m
2017-03-13 |  |  | Designer | SD og DCD for OC2 | 8:05 | 8:30 | 25m
|  |  | Reviewer | DCD for OC2 | 8:30 | 9:00 | 30m
|  |  | Reviewer | SD for OC2 | 9:00 | 10:00 | 1t
|  |  | Designer | SD og DCD for OC4 | 10:00 | 10:45 | 45m
|  |  | Reviewer | Testsuite OC1 | 10:45 | 11:15 | 30min
|  |  | Reviewer | SD for OC1 | 11:15 | 12:00 | 45min
|  |  | Designer | SD fir OC1 | 12:00 | 13:15 | 1t 15m
|  |  | Reviewer | DCD for OC1 | 13:15 | 13:55 | 40m
|  |  | Reviewer | Testsuite OC2 | 13:55 | 14:15 | 20m
2017-03-14 |  |  | Requirements Specifier | Usecase 7 - Formel + AD + Testcase | 8:15 | 9:40 | 1t 25m
|  |  | Requirements Specifier | Usecase 8 - DD + AD + Testcase | 10:00 | 11:30 | 1t 30m
|  |  | Reviewer | UC7 | 12:00 | 12:45 | 45m
|  |  | Reviewer | UC8 | 12:45 | 13:45 | 1t
|  |  | Reviewer | UC3 | 13:45 | 14:45 | 1t
|  |  | Reviewer | Review kode til OC1 | 14:45 | 15:10 | 25m
|  |  | Reviewer | Review kode til OC2 | 15:10 | 15:30 | 20m
2017-03-15 |  |  | Reviewer | Review SDD til UC7 | 9:45 | 10:00 | 15m
|  |  | Designer | Design UC7 om | 10:00 | 10:40 | 40m
|  |  | Implementer | Testsuite for OC5 | 10:40 | 12:45 | 2t 15m
|  |  | Implementer | Testsuite for OC7 - not possible | 12:45 | 13:45 | 1t
|  |  | Implementer | OC5 - Not possible - Design omarbejdes | 13:45 | 14:20 | 35m
|  |  | Implementer | OC7 | 14:25 | 15:15 | 50m
2017-03-17 |  |  | Implementer | OC7 | 8:15 | 9:15 | 1t
|  |  | Implementer | OC5 | 9:15 | 14:00 | 4t 45m
2017-03-20 |  |  | Implementer | GUI-design | 8:15 | 13:00 | 5t 45m
|  |  | Reviewer | OC9 review | 13:00 | 13:20 | 20m
|  |  | Implementer | GUI-design | 13:20 | 16:00 | 2t 40m
2017-03-21 |  |  | Test Analyst | Brugertest | 8:10 | 10:20 | 2t 10m
|  |  | Reviewer | OC15 | 10:20 | 10:40 | 20m
|  |  | Designer | OC15 | 10:40 | 13:00 | 2t 20m
|  |  | Designer | OC16 | 13:00 | 14:00 | 1t

## Hjælp til rollevalg
* Hvis du er i tvivl om din rolle, så kig i Appendiks A i "Rational Unified Process" (PDF side: 304 - 310) Bogen side 273 - 280)

## Deltagere
Morten K. Andersen
Steffen S. Andersen
Jeppe Damborg
Henrik S. Jørgensen
Tolga Y. Kücük
Ulla Larsen
Jurijs Mahtodujs
Christoffer A. Mørch
Maibritt R. Nielsen
Simon E.H. Nielsen
Nada H. A. Omer
Laura Poyner
Dennis K. Rasmussen
Dennis S. Rosenkilde
Allan Strange
Dan A. Toft

## Gyldige roller
Any Role
Business Designer
Business-Process Analyst
Capsule Designer
Change Control Manager
Configuration Manager
Course Developer
Database Designer
Deployment Manager
Designer
Graphic Artist
Implementer
Integrator
Management Reviewer
Process Engineer
Project Manager
Requirements Specifier
Review Coordinator
Reviewer
Software Architect
Stakeholder
System Administrator
System Analyst
Technical Writer
Test Analyst
Test Designer
Test Manager
Tester
Tool Specialist
User-Interface Designer