## Tidsregistrering
TIDSREGISTRERING FOR PTE-PROJEKTET (6-3-2017 - 24-3-2017)
Dato: | Navn: | Maibritt R. Nielsen | Rolle: |  | Aktivitet: | Starttid: | Sluttid: | Samlet tid brugt (timer):
2017-03-06 |  |  |  | Project Manager | Projektplan | 8.30 | 15.30
[5 empty] | Rollefordeling | 8.05 | 8.30
2017-03-07 |  |  |  | Requirements Specifier | Use case 1 | 8.15 | 10.30
[5 empty] | Test case UC 1 | 8.15 | 10.30
[5 empty] | Mock up UC 1 | 8.15 | 10.30
[5 empty] | Aktivitetsdiagram UC 5 | 10.30 | 11.30
[5 empty] | Mock up UC 5 | 10.30 | 11.30
[5 empty] | Dataordbog UC 5 | 10.30 | 11.30
|  |  |  | Any Role | Aktivitetsdiagram UC 5 | 12.00 | 13.10
[5 empty] | UC 1 full indskrevet | 13.10 | 14.30
|  |  |  | Reviewer | Review på UC 1 | 14.30 | 15.20
2017-03-08 |  |  |  | Reviewer | Review på DOM UC 1 | 08.15 | 10.20
|  |  |  | Reviewer | Review på AD UC 1 | 08.15 | 9.30
[5 empty] | Opdatering af DD | 10.20 | 11.05
[5 empty] | Ødelægge Java | 11.05 | 12.50
|  |  |  | Reviewer | Review AD UC 5 | 12.50 | 13.45
|  |  |  | Reviewer | Review UC 5 | 14.00 | 14.35
|  |  |  | Reviewer | Review DOM UC 5 | 14.35 | 15.12
2017-03-10 |  |  |  | Reviewer | Review AD UC 5 | 12.40 | 13.00
|  |  |  | Reviewer | Review UC 5 | 12.40 | 13.00
2017-03-13 |  |  |  | Reviewer | Review UC 5 | 08.15 | 8.45
|  |  |  | Reviewer | Review AD UC 5 | 8.45 | 10.15
[5 empty] | Test case OC 2 | 10.35 | 11.30
|  |  |  | Implementer | Implimentation OC 2 | 12.25 | 14.05
2017-03-14 |  |  |  | Requirements Specifier | UC 6 | 10.00 | 10.30
[5 empty] | UC 6 DD | 08.15 | 9.40
[5 empty] | DOM UC 6 | 10.15 | 10.30
|  |  |  | Tester | Junit test OC 4 | 13.30 | 14.50
|  |  |  | Requirements Specifier | DOM UC 6 | 14.55 | 15.05
2017-03-15 |  |  |  | Reviewer | Review OC 7 til UC 5 | 8.25 | 9.00
[5 empty] | SD for OC 7 | 9.20 | 10.45
[5 empty] | Skema for Anders | 10.50 | 12.45
|  |  |  | Reviewer | Review OC 7 | 13.16 | 15.05
|  |  |  | Reviewer | Review SSD 9 | 15.15 | 15.30
2017-03-17 |  |  |  | Implementer | Ændre i brugergrænseFladen | 8.20 | 11.20
2017-03-20 |  |  |  |  | OC 10 exporter pdf | 8.25 | 9.05
[5 empty] | DOM UC 9 | 8.25 | 9.05
[5 empty] | DOM samlet | 8.50 | 9.05
|  |  |  | Reviewer | Review OC 13 | 9.30 | 9.55
|  |  |  | Test Designer | Test suite OC 13 beregnBøjningsMoment | 10.05 | 10.55
[5 empty] | Dataorbog samling | 11.00 | 11.30
[5 empty] | Opgaver til Brugertest | 12.25 | 12.55
|  |  |  | Reviewer | Review på OC 8 test suite | 12.05 | 13.15
|  |  |  | Reviewer | Review på OC 11 DCD, SD | 13.15 | 14.30
2017-03-21 |  |  |  |  | Brugertest UC 1+2+4+5 | 8.15 | 9.30
|  |  |  | Implementer | Implimentation OC 8 | 10.05 | 11.10
|  |  |  | Reviewer | Review | 11.10 | 11.30
[5 empty] | OC 8 SD | 12.30 | 13.45
[5 empty] | Gui programmering | 14.00 | 15.30

## Hjælp til rollevalg
* Hvis du er i tvivl om din rolle, så kig i Appendiks A i "Rational Unified Process" (PDF side: 304 - 310) Bogen side 273 - 280)

## Deltagere
Morten K. Andersen
Steffen S. Andersen
Jeppe Damborg
Henrik S. Jørgensen
Tolga Y. Kücük
Ulla Larsen
Jurijs Mahtodujs
Christoffer A. Mørch
Maibritt R. Nielsen
Simon E.H. Nielsen
Nada H. A. Omer
Laura Poyner
Dennis K. Rasmussen
Dennis S. Rosenkilde
Allan Strange
Dan A. Toft

## Gyldige roller
Any Role
Business Designer
Business-Process Analyst
Capsule Designer
Change Control Manager
Configuration Manager
Course Developer
Database Designer
Deployment Manager
Designer
Graphic Artist
Implementer
Integrator
Management Reviewer
Process Engineer
Project Manager
Requirements Specifier
Review Coordinator
Reviewer
Software Architect
Stakeholder
System Administrator
System Analyst
Technical Writer
Test Analyst
Test Designer
Test Manager
Tester
Tool Specialist
User-Interface Designer