## Tidsregistrering
TIDSREGISTRERING FOR PTE-PROJEKTET (6-3-2017 - 24-3-2017)
Dato: | Navn: |  | Rolle: |  | Aktivitet: | Starttid: | Sluttid: | Samlet tid brugt (timer):
2017-03-06 | HS | Henrik Stensgaard |  | Project Manager | Risikoanalyse | 8:05 | 13:00 | 7.25
2017-03-06 | HS | Henrik Stensgaard |  | Business Designer | Use case skabelon | 13:00 | 15:10 | 2.1
2017-03-07 | HS | Henrik Stensgaard |  | Test designer | Use case 2 | 8:15 | 14:00 | 6.15
2017-03-07 | HS | Henrik Stensgaard |  | Test designer | Aktivitetsdiagram UC3 | 10:45 | 11:30 | 0.45
2017-03-07 | HS | Henrik Stensgaard |  | System Analyst | Opsætning Af Github | 11:30 | 12:00 | 0.3
2017-03-07 | HS | Henrik Stensgaard |  | Requirements Specifier | Dataordbog | 12:10 | 13:20 | 1.1
2017-03-07 | HS | Henrik Stensgaard |  | Reviewer | reviewet use case 1 | 14:00 | 15:30 | 1.3
2017-03-13 | HS | Henrik Stensgaard |  | Reviewer | reviewet test case operationskontakt 4 | 8:05 | 9:20 | 1.15
2017-03-13 | HS | Henrik Stensgaard |  | Requirements Specifier | Test case operationskontakt 2 | 10:35 | 11:30 | 0.55
2017-03-13 | HS | Henrik Stensgaard |  | Requirements Specifier | Unit test: Test case 3 (OC3) | 12:00 | 13:40 | 1.4
2017-03-13 | HS | Henrik Stensgaard |  | Requirements Specifier | Unit test: Test case 4 (OC4) | 13:45 | 14:15 | 1
2017-03-13 | HS | Henrik Stensgaard |  | Designer | Implementer OC4 | 14:20 | 15:30 | 1.1
2017-03-14 | HS | Henrik Stensgaard |  | Requirements Specifier | Aktivitetsdiagram UC6 | 8:30 | 9:10 | 0.4
2017-03-14 | HS | Henrik Stensgaard |  | Requirements Specifier | Dataordbog | 9:10 | 9:20 | 0.1
2017-03-14 | HS | Henrik Stensgaard |  | Test designer | Test case UC6 | 9:20 | 9:35 | 0.15
2017-03-14 | HS | Henrik Stensgaard |  | Test designer | Use case 9 | 9:35 | 9:50 | 0.25
2017-03-14 | HS | Henrik Stensgaard |  | Test designer | Test case UC9 | 9:50 | 10:30 | 0.4
2017-03-14 | HS | Henrik Stensgaard |  | Requirements Specifier | Opsætning Af PDF fil | 10:30 | 11:30 | 1
2017-03-14 | HS | Henrik Stensgaard |  | Reviewer | Revieweret Aktivitetsdiagram UC3 | 14:10 | 14:30 | 0.2
2017-03-14 | HS | Henrik Stensgaard |  | Project Manager | Risikoanalyse | 13:20 | 14:50 | 1.3
2017-03-17 | HS | Henrik Stensgaard |  | Designer | Sekvensdiagram erVaegtNormal | 9:10 | 9:20 | 0.1
2017-03-17 | HS | Henrik Stensgaard |  | Designer | Klassediagarm erVaegtNormal | 9:20 | 9:30 | 0.1
2017-03-17 | HS | Henrik Stensgaard |  | Designer | Sekvensdiagram erLaengdenNormal | 9:45 | 10:30 | 0.45
2017-03-17 | HS | Henrik Stensgaard |  | Designer | Klassediagarm erLaengdeNormal | 10:30 | 11:10 | 0.4
2017-03-20 | HS | Henrik Stensgaard |  | Designer | OperationsKontakt OC12 | 8:15 | 8:45 | 0.3
2017-03-20 | HS | Henrik Stensgaard |  | Reviewer | revieweret OC8 | 9:05 | 9:25 | 0.2
2017-03-20 | HS | Henrik Stensgaard |  | Test designer | Test suite 09 | 9:30 | 10:25 | 0.55
2017-03-20 | HS | Henrik Stensgaard |  | Designer | Klassediagram OC11 getsigmaref | 10:30 | 11:15 | 0.45
2017-03-20 | HS | Henrik Stensgaard |  | Designer | Sekvensdiagram OC11 getsigmaref | 11:15 | 11:30 | 0.15
2017-03-20 | HS | Henrik Stensgaard |  | Designer | Klassediagram OC11 getSikkerhedsFaktor | 12:10 | 12:25 | 0.15
2017-03-20 | HS | Henrik Stensgaard |  | Designer | Sekvensdiagram OC11 getSikkerhedsFaktor | 12:25 | 12:40 | 0.25
2017-03-21 | HS | Henrik Stensgaard |  | Reviewer | Review Kode til oc9, sikkerhedsfaktor | 14:15 | 15:00 | 0.45
2017-03-22 | HS | Henrik Stensgaard |  | Reviewer | Review kode til OC10 export til pdf | 8:20 | 8:35 | 0.15
2017-03-22 | HS | Henrik Stensgaard |  | Implementer | rettet OC4 og OC3 | 9:00 | 11:25 | 2.25
2017-03-22 | HS | Henrik Stensgaard |  | Implementer | Testcase halvprofilhøjde | 12:10 | 13:00 | 0.5
2017-03-22 | HS | Henrik Stensgaard |  | Implementer | Klassetest Normalkraft | 13:30 | 15:30 | 2
2017-03-23 | HS | Henrik Stensgaard |  | Implementer | rettet Junit test | 8:05 | 12:00 | 1.55
2017-03-23 | HS | Henrik Stensgaard |  | Implementer | Implementeret Arm classe og tilføjet | 12:30 | 15:30 | 2

## Hjælp til rollevalg
* Hvis du er i tvivl om din rolle, så kig i Appendiks A i "Rational Unified Process" (PDF side: 304 - 310) Bogen side 273 - 280)

## Deltagere
Morten K. Andersen
Steffen S. Andersen
Jeppe Damborg
Henrik S. Jørgensen
Tolga Y. Kücük
Ulla Larsen
Jurijs Mahtodujs
Christoffer A. Mørch
Maibritt R. Nielsen
Simon E.H. Nielsen
Nada H. A. Omer
Laura Poyner
Dennis K. Rasmussen
Dennis S. Rosenkilde
Allan Strange
Dan A. Toft

## Gyldige roller
Any Role
Business Designer
Business-Process Analyst
Capsule Designer
Change Control Manager
Configuration Manager
Course Developer
Database Designer
Deployment Manager
Designer
Graphic Artist
Implementer
Integrator
Management Reviewer
Process Engineer
Project Manager
Requirements Specifier
Review Coordinator
Reviewer
Software Architect
Stakeholder
System Administrator
System Analyst
Technical Writer
Test Analyst
Test Designer
Test Manager
Tester
Tool Specialist
User-Interface Designer