## Tidsregistrering
TIDSREGISTRERING FOR PTE-PROJEKTET (6-3-2017 - 24-3-2017)
Dato: | Navn: | Jeppe Damborg | Rolle: |  | Aktivitet: | Starttid: | Sluttid: | Samlet tid brugt (timer):
2017-03-06 |  |  |  | Any Role | Lav og færdigøre Tidsregistrering for PTE-projektet | 8:30 | 11:30
[5 empty] | Lav og færdigøre Dataordbog | 12:00 | 12:45
[5 empty] | Lav og færdigøre Visionsdokument skabelon | 13:20 | 13:40
4.3
2017-03-07 |  |  |  | Requirements Specifier | Domæne model over use case 2 (også use case 1) | 8:30 | 10:30
[5 empty] | Dataordbog for use case 2 (også for use case 1) | 8:30 | 10:30
[5 empty] | Mock up og test over use case 2( også for use case 1) | 8:30 | 10:30
[5 empty] | Aktivitetsdiagram for use case 4 | 10:30 | 11:30
[5 empty] | Dataordbog for use case 4 | 10:30 | 11:30
[5 empty] | Dataordbog for use case 2 (også for use case 1) | 12:00 | 15:00
[5 empty] | Dataordbog for use case 4 | 12:00 | 15:00
6
2017-03-08 |  |  |  | Reviewer | Krydstjekket use case 1 | 8:10 | 9:15
|  |  |  | Requirements Specifier | Integreret domæne model for use case 1 + 2 | 9:30 | 13:45
[5 empty] | Lavet review af domæne model for use case 5 | 14:25 | 14:50
5.55
2017-03-10 |  |  |  | Software Architect | Lavet design af OC3 | 8:05 | 10:20
|  |  |  | Requirements Specifier | Begynd at lave test suite for OC4 | 12:00 | 12:30
|  |  |  | Reviewer | Lavet review af OC artefakter | 10:20 | 11:30
3.55
2017-03-13 |  |  |  | Reviewer | Lavet review af test suite for OC4 | 8:22 | 9:15
[5 empty] | Lavet review af OC2 | 10:30 | 11:20
[5 empty] | Lavet review af OC4 | 12:07 | 13:34
|  |  |  | Requirements Specifier | Integreret Dom5 | 14:45 | 14:56
3.2
2017-03-14 |  |  |  | Test Analyst | Lavet brugertest på alpha brugergrænseflade | 8:05 | 11:00
|  |  |  | Requirements Specifier | Lavet OC 5 beregnSigmaN | 12:10 | 13:30
[5 empty] | Lavet Test Suite for OC7 beregnSigmaTau | 13:35 | 14:04
[5 empty] | Lavet Test Suite for OC5 beregnSigmaN | 14:45 | 14:50
5
2017-03-15 |  |  |  | Software Architect | Lavet design af OC6 | 8:16 | 10:26
|  |  |  | Reviewer | Lavet review af OC6 design | 10:55 | 11:20
[5 empty] | Lavet review af SSD3 | 11:20 | 11:27
|  |  |  | Implementer | Har Implementeret test case for OC6 | 12:05 | 13:05
[5 empty] | Har Implementeret design for OC6 | 13:05 | 13:44
|  |  |  | Software Architect | Har lavet SSD for UC9 | 13:50 | 14:00
|  |  |  | Reviewer | Lavet krydstjek af UC6 | 14:15 | 15:05
5.1

## Hjælp til rollevalg
* Hvis du er i tvivl om din rolle, så kig i Appendiks A i "Rational Unified Process" (PDF side: 304 - 310) Bogen side 273 - 280)

## Deltagere
Morten K. Andersen
Steffen S. Andersen
Jeppe Damborg
Henrik S. Jørgensen
Tolga Y. Kücük
Ulla Larsen
Jurijs Mahtodujs
Christoffer A. Mørch
Maibritt R. Nielsen
Simon E.H. Nielsen
Nada H. A. Omer
Laura Poyner
Dennis K. Rasmussen
Dennis S. Rosenkilde
Allan Strange
Dan A. Toft

## Gyldige roller
Any Role
Business Designer
Business-Process Analyst
Capsule Designer
Change Control Manager
Configuration Manager
Course Developer
Database Designer
Deployment Manager
Designer
Graphic Artist
Implementer
Integrator
Management Reviewer
Process Engineer
Project Manager
Requirements Specifier
Review Coordinator
Reviewer
Software Architect
Stakeholder
System Administrator
System Analyst
Technical Writer
Test Analyst
Test Designer
Test Manager
Tester
Tool Specialist
User-Interface Designer