## Tidsregistrering
TIDSREGISTRERING FOR PTE-PROJEKTET (6-3-2017 - 24-3-2017)
Dato: | Navn: | Ulla Larsen | Rolle: |  | Aktivitet: | Starttid: | Sluttid: | Samlet tid brugt (timer):
2017-03-06 |  |  |  | Project Manager | Tidsregistrering skabelon | 8.15 | 11.30 | 3.15
[5 empty] | Dataordbog skabelon | 12.00 | 12.30 | 0.30
[5 empty] | Visionsdokument skabelon | 13.20 | 13.40 | 0.20
2017-03-07 |  |  |  | Requirements Specifier | UC1 - Domænemodel, Dataordbog, Mockups | 8.45 | 10.30 | 1.45
[5 empty] | UC3 - Aktivitetsdiagram, Dataordbog, Mockups | 10.30 | 11.30 | 1.00
|  |  |  | Tester | Brugertest | 12.00 | 13.00 | 1.00
[5 empty] | Udfør brugertest | 13.00 | 14.10 | 1.10
[5 empty] | Design GUI fra UC1 og UC2 | 14.30 | 15.30 | 1.00
2017-03-08 |  |  |  | Reviewer | Krydstjek UC1 | 8.15 | 11.05 | 2.50
|  |  |  | Any Role | Rådgiver for Integrer DOM2 | 11.05 | 11.30 | 0.25
|  |  |  | Requirements Specifier | OC 2, Opdatering af SSD UC 2 | 13.00 | 14.40 | 1.40
2017-03-12 |  |  |  | Test Designer | Test Suite 3 | 17.00 | 18.00 | 1.00
2017-03-21 |  |  |  | Reviewer | Review design OC 10 | 8.20 | 9.20 | 1.00
|  |  |  | Reviewer | Review design OC 08 | 9.30 | 10.00 | 0.30
|  |  |  | Implementer | GUI: rette horisontal/vertikal til vandret/lodret | 10.10 | 10.20 | 0.10
|  |  |  | Implementer | GUI: tilføje trekantstegning med "mangler input" | 10.30 | 12.00 | 1.30
|  |  |  | Reviewer | Review design OC 14 | 12.30 | 13.00 | 0.30
|  |  |  | Reviewer | Review design kode OC 9 | 14.15 | 15.00 | 0.45

## Hjælp til rollevalg
* Hvis du er i tvivl om din rolle, så kig i Appendiks A i "Rational Unified Process" (PDF side: 304 - 310) Bogen side 273 - 280)

## Deltagere
Morten K. Andersen
Steffen S. Andersen
Jeppe Damborg
Henrik S. Jørgensen
Tolga Y. Kücük
Ulla Larsen
Jurijs Mahtodujs
Christoffer A. Mørch
Maibritt R. Nielsen
Simon E.H. Nielsen
Nada H. A. Omer
Laura Poyner
Dennis K. Rasmussen
Dennis S. Rosenkilde
Allan Strange
Dan A. Toft

## Gyldige roller
Any Role
Business Designer
Business-Process Analyst
Capsule Designer
Change Control Manager
Configuration Manager
Course Developer
Database Designer
Deployment Manager
Designer
Graphic Artist
Implementer
Integrator
Management Reviewer
Process Engineer
Project Manager
Requirements Specifier
Review Coordinator
Reviewer
Software Architect
Stakeholder
System Administrator
System Analyst
Technical Writer
Test Analyst
Test Designer
Test Manager
Tester
Tool Specialist
User-Interface Designer